## Sheet1
Agile Project Plan
Project Name
Project Manager
Project Deliverable
Scope Statement
Start Date
End Date
Overall Progress | 20
Task Name | Responsible | Start | End | Days | Status
Sprint 1 |  | 2017-03-27 | 2017-04-03 | 1900-01-06 | Complete
Documentation | All Members | 2017-03-27 | 2017-04-03 | 1900-01-06 | Complete
Sprint 2 |  | 2017-04-03 | 2017-04-17 | 1900-01-13 | Complete
black box test | shokoufeh | 2017-04-03 | 2017-04-13 | 1900-01-09 | finished
index.html | shokoufeh/arman | 2017-04-03 | 2017-04-16 | 1900-01-12 | fnished
ieeeSearchButton/ieeeSearchBar | shokoufeh /arman | 2017-04-03 | 2017-04-13 | 1900-01-09 | finished
ieeeSearchPage | shokoufeh/arman | 2017-04-03 | 2017-04-09 | 1900-01-05 | finished
simple design | shokoufeh | 2017-04-10 | 2017-04-16 | 1900-01-05 | finished
wordCloudPage | shokoufeh | 2017-04-03 | 2017-04-16 | 1900-01-12 | finished
|  | 2017-04-14 | 2017-04-16 | 1900-01-01 | Not started
|  | 2017-04-03 | 2017-04-17 | 1900-01-13 | Not started
Sprint 3 |  | 2017-04-17 | 2017-04-27 | 1900-01-09 | Not started
|  | 2017-04-17 | 2017-04-21 | 1900-01-03 | Not started
Task 9 | Matthew | 2017-04-22 | 2017-04-26 | 1900-01-03 | Not started
Task 10 | Brian | 2017-04-17 | 2017-04-21 | 1900-01-03 | Not started
Task 11 | Shokoufeh | 2017-04-17 | 2017-04-21 | 1900-01-03 | Not started
Task 12 | Shokoufeh | 2017-04-22 | 2017-04-26 | 1900-01-03 | Not started
Task 13 | Arman | 2017-04-17 | 2017-04-21 | 1900-01-03 | Not started
Task 14 | Arman | 2017-04-22 | 2017-04-26 | 1900-01-03 | Not started
Task 15 | Brian | 2017-04-22 | 2017-04-26 | 1900-01-03 | Not started
Documentation | All Members | 2017-04-17 | 2017-04-27 | 1900-01-09 | Not started
Create an Agile Project Plan in Smartsheet
Formulas:
Start = [Start, row below]
Days = [End]-[Start]